Terms of Reference (ToR)

Consultancy Services -

Coordination of the Red List assessment of Western Mediterranean bees

**IUCN Centre for Mediterranean Cooperation**

**Closing Date and Time:1 September 2023, 17:00 (CET)**

PART 1 – INSTRUCTIONS TO PROPOSERS AND PROPOSAL CONDITIONS

* 1. About IUCN

IUCN is a membership Union uniquely composed of both government and civil society organisations. It provides public, private and non-governmental organisations with the knowledge and tools that enable human progress, economic development and nature conservation to take place together.

Created in 1948, IUCN is now the world’s largest and most diverse environmental network, harnessing the

knowledge, resources and reach of 1,400 Member organisations and some 15,000 experts. It is a leading provider of conservation data, assessments and analysis. Its broad membership enables IUCN to fill the role of incubator and trusted repository of best practices, tools and international standards.

IUCN provides a neutral space in which diverse stakeholders including governments, NGOs, scientists,

businesses, local communities, indigenous peoples’ organisations and others can work together to forge and

implement solutions to environmental challenges and achieve sustainable development.

Working with many partners and supporters, IUCN implements a large and diverse portfolio of conservation projects worldwide. Combining the latest science with the traditional knowledge of local communities, these projects work to reverse habitat loss, restore ecosystems and improve people’s well-being.

[www.iucn.org](http://www.iucn.org)

<https://twitter.com/IUCN/>

* 1. Summary of the Requirement

IUCN invites you to submit a Proposal for Consultancy Services to coordinate the Red List assessment of Western Mediterranean bees. The detailed Terms of Reference can be found in Part 2 of these TORs.

* 1. The procurement process

The following key dates apply to these ToRs:

|  |  |
| --- | --- |
| **ToRs Issue Date** | 22 August 2023 |
| **ToRs Closing Date and Time** | 1 September 2023 17:00 (CET time) |
| **Estimated Contract Award Date** | 15 September 2023 |

* 1. Conditions

IUCN is not bound in any way to enter into any contractual or other arrangement with any Proposer as a result of issuing these ToRs. IUCN is under no obligation to accept the lowest priced Proposal or any Proposal. IUCN reserves the right to terminate the procurement process at any time prior to contract award. By participating in these ToRs, Proposers accept the conditions set out in these ToRs.

IUCN requires Proposers to refrain from corrupt and fraudulent/prohibited practices in participating in this procurement. To this end, **Proposers must sign the “Proposer’s Declaration” at the end of this document and include it in their Proposal.**

Proposers shall permit IUCN to inspect all accounts, records and other documents relating to the submission of the Proposal and contract performance (in case of an award), and to have them audited by auditors appointed by IUCN.

* 1. Queries and questions during the ToRs period

Proposers are to direct any queries and questions regarding the ToRs to the above IUCN Contact. No other IUCN personnel are to be contacted in relation to these ToRs.

As far as possible, IUCN will issue the responses to any questions, suitably anonymised, to all Proposers. If you consider the content of you question confidential, you must state this at the time the question is posed.

* 1. Amendments to ToRs documents

IUCN may amend the ToRs documents by issuing notices to that effect to all Proposers and may extend the ToRs closing date and time if deemed appropriate.

* 1. Proposal lodgement methods and requirements

Proposers must submit their Proposal to IUCN no later than **1 September 203 17:00 (CET time) by email to** [medspecies@iucn.org](mailto:medspecies@iucn.org) (with the reference "RL WEST MED BEES"). Electronic copies are to be submitted in PDF format.

Proposals must be prepared in English and in the format stated in Part 3 of these ToRs.

* 1. Late and Incomplete Proposals

Any Proposal received by IUCN later than the stipulated ToRs closing date and time, and any Proposal that is incomplete, will not be considered. There will be no allowance made by IUCN for any delays in transmission of the Proposal from Proposer to IUCN.

* 1. Withdrawals and Changes to the Proposal

Proposals may be withdrawn or changed at any time prior to the ToRs closing date and time by written notice to the IUCN contact. No changes or withdrawals will be accepted after the ToRs closing date and time.

* 1. Validity of Proposals

Proposals submitted in response to these ToRs are to remain valid for a period of 90 calendar days from the ToRs closing date.

* 1. Evaluation of Proposals

The evaluation of Proposals shall be carried out exclusively with regards to the evaluation criteria and their relative weights specified in part 3 of these ToRs.

PART 2 – TERMS OF REFERENCE

* 1. Background

As part of its Biodiversity Knowledge and Action working plan, IUCN Med will assess the conservation status of a selection of bees’ species mainly occurring in Western part of the Mediterranean Basin.

The results will complement IUCN activities under project SAFEGUARD (Horizon 2020 Grant Agreement No 101003476) which aims to make a step change in the protection and restoration of European pollinators, their essential services and the wider co-benefits they provide, thereby making a significant contribution to the ambitious EU Green Deal and the EU Biodiversity Strategy for 2030.

* 1. Scope of the Consultancy

The objective of this consultancy is to provide technical support the data collection and assessment for a selection of 200 species of bees (Families Andrenidae, Apidae, Colletidae, Halictidae, Megachilidae and Melittidae) from Western part of the Mediterranean Basin.

The consultant will be responsible for:

1. Reviewing and updating the list of bees which are endemic to the Western Mediterranean region with enough information to be potentially assessed for the Red List
2. Collecting, databasing and reviewing data for all the bees species listed in annex I, including information regarding the taxonomy, geographic range, distribution status (with corresponding range maps), population size an trend, preferred habitats, general ecology, major threats and current and future conservation needed to perform for all species
3. Entering data into IUCN SIS database for all species
4. Engaging with the assessment review process and responding to review comments and necessary revisions
5. 5.Lead in collaboration with IUCN the production of a short report summarizing the main results of the assessment
6. 6.Submit all deliverables no later than the agreed deadlines as set out in the annex I
   1. Methodology

The following steps will be undertaken:

1. **Selection of Species**

The consultant shall identify a set of criteria to select a list of 200 species which are endemic to Western part of the Mediterranean Basin.

1. **Species Red List Documentation**

The consultant will:

- Take responsibility for developing the preliminary assessments and collecting all the data that underpin the assessment in line with the IUCN RL methodology. For this, the consultant with the support of IUCN, will contact regional and national experts to provide additional relevant data

- Complete the IUCN RL documentation for the species to be assessed

o This work will involve completing for each allocated species all mandatory fields in SIS.

o Every effort should be made to ensure all available information has been sourced and included. This task must be completed according to the “Documentation Standards and Consistency Checks for IUCN Red List Assessments and Species Accounts” [IUCN Red List of Threatened Species.](https://www.iucnredlist.org/resources/supporting-information-guidelines)

1. **Species maps**

- Produce digital GIS distribution maps for all the species

- The distribution map should be prepared following the mapping standards and the documentation standards and consistency checks for IUCN Red List Assessments and species accounts”

1. **Preliminary RL status**

- Assess the IUCN RL status for each of the species assigned in the IUCN SIS database

- This task must be completed according to the IUCN Red List Categories and Criteria.

1. **Assessment review workshops**

- Lead and participate in regional assessment review workshops where a selection of the species will be reviewed. All preliminary assessments must be ready prior the date of the workshop. The workshops will be organized with the technical and logistic support of IUCN.

1. **Photos of the species assessed, their habitats and main threats should be provided where possible.**

**-** For each image contribute/copyright owner, a completed image use permission form should be provided, stating how the image may be used by IUCN.

1. **Publication**

- The consultant will co-author a publication “The conservation status of endemic wild bees in Western part of the Mediterranean Basin?’. IUCN will brief and provide detailed instructions on the content of the publication. It is anticipated that the publication authorship will be inclusive of all significant experts and contributing IUCN staff.

1. **Communication of results and synergies with Safeguard**

- Provide graphic and photographic materials for communication, integrate and analyse results into safeguard products

* 1. Key Deliverables and Payment

|  |  |
| --- | --- |
| ***Key tasks and deliverables*** | ***Deadline***  ***(after signature of contract)*** |
| D1. List of taxa | ***30 September 2023*** |
| D2. Draft assessments in SIS | ***January 2024*** |
| D3. External validation | ***January 2024*** |
| D4. Assessment workshop | ***End January 2024*** |
| D5 Revised assessments | ***February 2024*** |
| D6 consistency checking | ***March 2024*** |
| D7 final assessments and maps | ***April 2024*** |
| D8 writing report | ***May 2024*** |
| D9 Integration of results and synergies with Safeguard | ***June 2024*** |

*All final decisions concerning the successful delivery and quality of deliverables will be made by IUCN Centre for Mediterranean Cooperation (IUCN-Med). The consultant shall schedule time in the workplan for reviewing drafts and implementing feedback based on discussions with IUCN-Med.*

**The maximum budget available for this consultancy is €20,000 (VAT and all taxes incl. \*)**

\* *VAT and other taxes are included in the abovementioned amount. IUCN is not acting as a business or professional nature entity for VAT purposes and therefore the consultant should charge in its invoices the VAT or analogous tax accordingly. In case that the consultant is exempt of VAT or equivalent tax in its jurisdiction, it should include a note in the invoice document informing of this issue and mentioning the law that applies*

* 1. Supervision and Collaboration

The consultant will work under the supervision of the Communications specialist at IUCN Centre for Mediterranean Cooperation (IUCN-Med). IUCN Med will have the final decision concerning successful delivery and quality of all deliverables. The outline of all deliverables should be agreed with IUCN-Med team ahead of the work. Consultants should build time for discussion before starting each deliverable and for review and sign-off feedback of the different deliverables.

IUCN-Med will provide contact or access to relevant contacts to carry out the assignment.

* 1. Timeline

The timeframe for the completion of this work will be from the signature of the contract until 31 August 2024 at the latest (12 months). The logistical plan and preparation of the activity/s, as well as relevant information, will be shared with IUCN-Med to ensure adequate follow-up.

* 1. Profile of the consultants

The company/expert(s)/organization involved in this consultancy must have knowledge and experience in IUCN Red List assessments and the relevant taxonomic group as well.

Consultants are expected to work closely with the IUCN-Med, and be flexible to adapt to changes.

PART 3 – INFORMATION TO BE PROVIDED BY PROPOSERS

By participating in these ToRs, Proposers are indicating their acceptance to be bound by the conditions set out in these ToRs.

Submitted information will be used in the evaluation of Proposals. Proposers are discouraged from sending additional information, such as sales brochures, that are not specifically requested.

*Selection criteria*

Activity proposals will be evaluated according to the following criteria:

- Proposed working plan

- Team experience.

- Examples of previous work.

- Financial offer

Declaration

Please read and sign the corresponding Declaration at the end of this document and include it in your proposal.

Technical proposal

Applicants are expected to submit a technical proposal including CVs to justify the experience of the team/person

Financial proposal

**Prices include all costs**

Submitted rates and prices are deemed to include all costs, insurances, taxes, fees, expenses, liabilities, obligations, risk and other things necessary for the performance of the Requirement. Any charge not stated in the Proposal as being additional, will not be allowed as a charge against any transaction under any resultant Contract.

**Applicable Goods and Services Taxes**

Proposal rates and prices shall be inclusive of Value Added Tax.

**Currency of proposed rates and prices**

Unless otherwise indicated, all rates and prices submitted by Proposers shall be in Euros.

**Rates and Prices**

Proposers are required to submit a fixed and firm price for the total of the services.

# PROPOSER’S Declaration FOR SELF-EMPLOYED WORKERS

I, the undersigned, hereby confirm that I am self-employed and able to provide the service independent of any organisation or other legal entity.

Full name (as in passport):

Home or Office (please delete as appropriate) Address (incl. country):

I hereby authorise IUCN to store and use the information included in the attached Proposal for the purpose of evaluating Proposals and selecting the Proposal IUCN deems the most favourable, including Personal Data as defined by the European Union’s General Data Protection Regulation (GDPR). I acknowledge that IUCN is required to retain my Proposal in its entirety for 10 years after then end of the resulting contract and make this available to internal and external auditors and donors as and when reasonably requested.

I further confirm that the following statements are correct:

1. I am legally registered as self-employed in accordance with all applicable laws.
2. I am fully compliant with all my tax and social security obligations.
3. I am free of any real or perceived conflicts of interest with regards to IUCN and its Mission.
4. I agree to declare to IUCN any real or perceived emerging conflicts of interests I may have concerning IUCN. I acknowledge that IUCN may terminate any contracts with me that would, in IUCN sole discretion, be negatively affected by such conflicts of interests.
5. I have never been convicted of grave professional misconduct or any other offence concerning my professional conduct.
6. I have never been convicted of fraud, corruption, money laundering, supporting terrorism or involvement in a criminal organisation.
7. I acknowledge that engagement in fraud, corruption, money laundering, supporting terrorism or involvement in a criminal organisation will entitle IUCN to terminate any and all contracts with me with immediate effect.
8. I am not included in the UN Security Council Sanctions List, EU Sanctions Map, US Office of Foreign Assets Control Sanctions List, or the World Bank listing of ineligible firms and individuals. I agree that I will not provide direct or indirect support to firms and individuals included in these lists.
9. I have not been, am not, and will not be involved or implicated in any violations of Indigenous Peoples’ rights, or injustice or abuse of human rights related to other groups or individuals, including forced evictions, violation of fundamental rights of workers as defined by the International Labour Organization’s (ILO) Declaration on the Fundamental Principles and Rights at Work, child labour, sexual exploitation, sexual abuse, or sexual harassment.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

<Date and Signature>

# PROPOSER’ Declaration FOR COMPANIES

I, the undersigned, hereby confirm that I am an authorised representative of the following organisation:

Registered Name of Organisation (the “Organisation”): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Registered Address (incl. country): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Year of Registration:\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

I hereby authorise IUCN to store and use the information included in the attached Proposal for the purpose of evaluating Proposals and selecting the Proposal IUCN deems the most favourable. I acknowledge that IUCN is required to retain the Proposal in its entirety for 10 years after then end of the resulting contract and make this available to internal and external auditors and donors as and when reasonably requested.

Where the Proposal includes Personal Data as defined by the European Union’s General Data Protection Regulation (GDPR), I confirm that the Organisation has been authorised by each Data Subject to share this Data with IUCN for the purposes stated above.

I further confirm that the following statements are correct:

1. The Organisation is duly registered in accordance with all applicable laws.
2. The Organisation is fully compliant with all its tax and social security obligations.
3. The Organisation and its staff and representatives are free of any real or perceived conflicts of interest with regards to IUCN and its Mission.
4. The Organisation agrees to declare to IUCN any real or perceived emerging conflicts of interests it or any of its staff and representatives may have concerning IUCN. The Organisation acknowledges that IUCN may terminate any contracts with the Organisation that would, in IUCN sole discretion, be negatively affected by such conflicts of interests.
5. None of the Organisation’s staff has ever been convicted of grave professional misconduct or any other offence concerning their professional conduct.
6. Neither the Organisation nor any of its staff and representatives have ever been convicted of fraud, corruption, money laundering, supporting terrorism or involvement in a criminal organisation.
7. The Organisation acknowledges that engagement by itself or any of its staff in fraud, corruption, money laundering, supporting terrorism or involvement in a criminal organisation will entitle IUCN to terminate any and all contracts with the Organisation with immediate effect.
8. The Organisation is a going concern and is not bankrupt or being wound up, is not having its affairs administered by the courts, has not suspended business activities, is not the subject of proceedings concerning those matters, or in any analogous situation arising from a similar procedure provided for in national legislation or regulations.
9. The Organisation complies with all applicable environmental regulatory requirements or other legal requirements relating to sustainability and environmental protection.
10. The Organisation is not included in the UN Security Council Sanctions List, EU Sanctions Map, US Office of Foreign Assets Control Sanctions List, or the World Bank listing of ineligible firms and individuals. The Organisation agrees that it will not provide direct or indirect support to firms and individuals included in these lists.
11. The Organisation has not been, is not, and will not be involved or implicated in any violations of Indigenous Peoples’ rights, or injustice or abuse of human rights related to other groups or individuals, including forced evictions, violation of fundamental rights of workers as defined by the International Labour Organization’s (ILO) Declaration on the Fundamental Principles and Rights at Work, child labour, sexual exploitation, sexual abuse, or sexual harassment.

\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

<Date and Signature of authorised representative of the Proposer>

< Name and position of authorised representative of the Proposer >